## Sheet1
	- Samiksha Bagmar
	- Mukesh Vakude
	- Both
	-No work

	Project Title -		Pucsd Blog

	Project Description -			This project is for pucsd student which involve information about languages,placement questions,company info and question answer
				pattern for students where student can upload there question and anyone which is successfully register for blog can able to answer
				those question.

	Project Scope -
			1.Only limited to pucsd student.
			2. None of the student is able to delete other student’s post ,only the student who post it and admin of our website
			3.Home page include 3 blog-
				a) Language blog
				- Theory
				- Practical
				b) Placement blog
				- Company info
				- Placement Question
				- Alumini experience
				c) Question Answer blog

DATE	March
	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
TASK						Manual Design of project	Registration page with validation	Login page		Home PAGE					Language Blog On Home Page					Placement Blog On Home page

	April
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
TASK						Question Answer Blog On Home Page