## Sheet1
	16160 : Mukesh Vakude
	17202 : Samiksha Bagmar

	Project Title – Pucsd Blog

Sr no	Risk	Probability	Impact	RMMM (Risk Mitigation Monitoring and Management)
1	If question answer by student increases beyond system storage they it provide risk related storage of all data	0.5	4	1.We try remove dublicate answer / data.
				2.By keeping only relevent data on the basis of comment / feedback.
				3.We use cloud for storing data.
2	If anyone is able to delete any other student post.	0.2	1	We provide access only to the student who post it and admin of system

3	If any other student outside from pucsd try to register/login as pucsd student.	0.3	1	We validate email id of student with email which is given by sysadmin,

4	Password security.	0.8	5	We store password in encrypted format which is only decreapted by admin

5	If techology we use like mysql to store database is get crashed.	0.6	4	After each valid student we store it in cloud so if database get crashed we fetch from cloud